## Introduction
INTRODUCTION
In this spreadsheet, you will be able to assess potential risks for a deep geothermal project. It was developed by BRGM as part of the H2020 project GEORISK. It is dedicated to professionals of the field of deep geothermal energy. There are several sheets in this spreadsheet: - Introduction: the sheet you are currently reading - Risk identification: in this sheet, you can select and adapt the list of risks that will be considered in the assessment - Rating tables: allow the user to personalize the ratings used in the assessment - Risk assessment: in this sheet, you will assign scores to each risk; there is the possibility to perform two successive assessments - Plots : graphical display of the scores for the first assessment - Re-assessment plots: graphical display of the scores for the second assessment - PlotMatrix_dots: risk matrix display of the results for a selection of risks - PlotMatrix_Heat: risk matrix display of all the risks with IDs - Help: This tab will provide guidance for performing the assessment and using the results The spreadsheet is entirely open so you are free to make any change you want, just beware that changing formulas might break some features.
Thank you for your interest in our work. You can get more information by visiting:
www.georisk-project.eu
You can provide feedback for improving this spreadsheet either by mail or by submitting an issue on the GitHub page:
https://github.com/ThomasLeGuenan/Georisktool/issues
Credit: Georiskreport v2.1 Authors: Thomas Le Guénan, Annick Loschetter, Julie Maury (BRGM), Ferid Seyidov (Gec-Co) Date: 08/2021
contact:
t.leguenan@brgm.fr

## Risk identification
Date | [5 empty] | 2020-01-01
Name of project | [5 empty] | INSERT THE NAME OF YOUR PROJECT
Version of assessment | [5 empty] | 1
Additional details | [5 empty] | 1
Topic | ID | IE* | DT* | ED* | PC* | Link | Description | EPA* | HSE* | Pre-screnning | Comments
Managerial and Social-Economic | A-1 |  | X | X | X | (Info) | External natural hazards damaging the infrastructure | X | X | 1 |  | 1
| A-2 |  | X | X | X | (Info) | Anthropogenic hazard damaging the infrastructure | X | X | 1 |  | 2
| B-1 |  | X | X | X | (Info) | Changes in policies, laws, taxes and regulations put development/economy in jeopardy | X |  | 1 |  | 3
| B-2 | X | X | X |  | (Info) | Lack of financing for the next phases | X |  | 1 |  | 4
| B-3 | X | X | X |  | (Info) | Low social acceptance put barrier to development | X |  | 1 |  | 5
| B-4 |  | X | X |  | (Info) | Public opposition against nuisances from the exploitation | X |  | 1 |  | 6
| B-6 | X | X | X |  | (Info) | Lack or loss of clients | X |  | 1 |  | 7
| B-8 | X | X | X |  | (Info) | Significant changes of energy costs | X |  | 1 |  | 8
| C-1 |  | X | X | X | (Info) | Low financing for work leading to low safety standards |  | X | 1 |  | 9
| B-5 |  | X | X |  | (Info) | Unanticipated delays and costs in operations (materials, services, maintenance) | X |  | 1 |  | 10
| C-2 |  | X |  |  | (Info) | Suboptimal design of well leads to reduced flow rate | X |  | 1 |  | 11
| C-3 | X | X | X | X | (Info) | Best practices not applied (data acquisition, modelling, decision making, design of wells / plants, construction) | X | X | 1 |  | 12
| C-4 |  | X |  |  | (Info) | Unsuitable contracts (roles and responsibility not clearly defined) leading to suboptimal performance or exploding costs | X | X | 1 |  | 13
| C-8 |  | X | X |  | (Info) | Organization is not experienced / financially robust enough for the challenge | X |  | 1 |  | 14
| B-9 | X | X | X |  | (Info) | The research or exploitation permit is changed in favor of another resource | X |  | 1 |  | 15
| C-9 | X |  | X |  | (Info) | Demand analysis and forecast are inaccurate | X |  | 1 |  | 16
Operation and Geology | D-1 |  | X |  |  | (Info) | Flow rate lower than expected (reservoir) | X |  | 1 |  | 17
| D-2 |  |  | X |  | (Info) | Flow rate degrades over time | X |  | 1 |  | 18
| D-3 |  | X |  |  | (Info) | Temperature lower than expected (reservoir) | X |  | 1 |  | 19
| D-4 |  |  | X |  | (Info) | Temperature degrades too quickly | X |  | 1 |  | 20
| D-5 |  | X |  |  | (Info) | Pressure lower/higher than expected | X |  | 1 |  | 21
| D-6 |  |  | X |  | (Info) | Pressure is changing during the operation in an unexpected way | X |  | 1 |  | 22
| B-7 |  | X | X | X | (Info) | Neighbouring operators cause negative changes to the reservoir parameters. | X |  | 1 |  | 23
| D-7 |  | X | X | X | (Info) | Fluid chemistry/ gas content / physical properties are different from expected | X | X | 1 |  | 24
| F-6 |  |  | X |  | (Info) | NCG Production | X |  | 1 |  | 25
| C-5-a |  | X | X |  | (Info) | Human error leading to failure during work (including either insufficient background and/or regulations) [Op&Geology] | X |  | 1 |  | 26
| D-8 |  |  | X |  | (Info) | Fluid chemistry/ gas content / physical properties change | X | X | 1 |  | 27
| D-9 |  | X |  |  | (Info) | Target formation is missing in the well (unexpected geology, insufficient exploration) | X |  | 1 |  | 28
| D-10 |  | X |  |  | (Info) | Target formation has no/insufficient fluid for commercial production | X |  | 1 |  | 29
| D-11 |  | X |  |  | (Info) | Geological lithology or stratigraphy is different than expected | X |  | 1 |  | 30
| D-12 |  | X | X | X | (Info) | Excessive scaling in the geothermal loop | X |  | 1 |  | 31
| D-13 |  | X | X | X | (Info) | Excessive corrosion in the geothermal loop | X |  | 1 |  | 32
| D-14 |  |  | X |  | (Info) | Particle production ("sanding") | X |  | 1 |  | 33
| D-15 |  |  | X |  | (Info) | Hydraulic connectivity between wells is insufficient for commercial use | X |  | 1 |  | 34
| D-16 |  | X | X |  | (Info) | Re-injection of the fluid is more difficult than expected | X |  | 1 |  | 35
| D-17 |  |  | X |  | (Info) | Degradation of the reservoir (structure, properties, deteriorating whole-scale further commercial utilization) | X |  | 1 |  | 36
| F-8-a |  | X | X | X | (Info) | Loss of integrity of surface equipments (leakage from the tanks, pipeline, heat-exchanger, etc.) [Operation&Geology] | X | X | 1 |  | 37
Drilling | E-1 |  | X |  |  | (Info) | Fluid losses leading to severe technical issues | X | X | 1 |  | 38
| C-7 |  | X |  |  | (Info) | Damage to the well/reservoir while drilling or testing | X | X | 1 |  | 39
| E-2 |  | X |  |  | (Info) | Wellbore instability | X |  | 1 |  | 40
| E-3 |  | X |  |  | (Info) | Trajectory issues (deviation from target) | X |  | 1 |  | 41
| F-8-b |  | X |  |  | (Info) | Loss of integrity of surface equipments (leakage from the mud mud pit; well head and etc.) [Drilling] | X | X | 1 |  | 42
| F-7 |  | X | X |  | (Info) | Loss of integrity of the wellbore (connection of well fluid with surface; inter layer fluid connection; etc.) | X |  | 1 |  | 43
| C-6 |  | X |  |  | (Info) | Wrong choice of stimulation fluids or techniques damaging the reservoir/well | X |  | 1 |  | 44
| E-7 |  | X | X |  | (Info) | Issues in transporting/handling radioactive sources for logging | X | X | 1 |  | 45
| E-8 |  |  | X |  | (Info) | Technical failure of the equipment | X |  | 1 |  | 46
| E-9 |  | X |  |  | (Info) | Well casing collapse | X |  | 1 |  | 47
| F-1 |  | X | X | X | (Info) | Blowouts | X | X | 1 |  | 48
| F-2 |  | X | X | X | (Info) | Fluid communication between different formations due to ineffective isolation of the well | X | X | 1 |  | 49
| F-3 |  | X | X |  | (Info) | Induced seismicity (above sensitivity level) | X | X | 1 |  | 50
| F-4 |  | X | X | X | (Info) | Surface subsidence or uplift | X | X | 1 |  | 51
| F-5 |  | X | X |  | (Info) | Toxic emissions due to gases and fluids produced in-situ | X | X | 1 |  | 52
| C-5-b |  | X | X | X | (Info) | Human error leading to failure during work (including either insufficient background and/or safety regulations) [Drilling] | X | X | 1 |  | 53
| E-5 |  | X | X | X | (Info) | Technical failure/difficulties during drilling (due to any additional causes that were not mentioned) | X |  | 1 |  | 54
New risks | N-1 |  | X |  |  | New risks | My new risk | X | X | 1 |  | 55
| N-2 |  | X |  |  | New risks | My new risk 2 | X | X | 1 |  | 56
| N-3 |  | X |  |  | New risks | My new risk 3 | X |  | 1 |  | 57
| N-4 |  | X |  |  |  | My new risk 4 | X |  | 0 |  | 0
| N-5 |  | X |  |  |  | My new risk 5 | X | X | 0 |  | 0
| N-6 |  | X | X |  |  | My new risk 6 | X |  | 0 |  | 0
| N-7 |  | X |  |  |  | My new risk 7 | X |  | 0 |  | 0
| N-8 |  | X | X |  |  | My new risk 8 | X | X | 0 |  | 0
| N-9 |  |  | X |  |  | My new risk 9 | X |  | 0 |  | 0
| N-10 | [5 empty] | My new risk 10 |  |  | 0 |  | 0
| N-11 |  | X |  |  |  | My new risk 11 | X |  | 0 |  | 0
| N-12 |  | X |  |  |  | My new risk 12 | X |  | 0 |  | 0
| no risk in this category | [8 empty] | 0
The category of your new risks can be assigned to existing categories or remain in "new risks", by using the list in this column
Select or deselect risks by changing this column."1" select the risk; "0" deselect the risk.
You can freely rename the risk as well in order to adapt it to your case.
Click on the link "info" to get more information from the georisk risk register
At the end of the list, you have additional lines to add new risks
Important: do not modify this list after the assessment or the scores will not correspond anymore; use a new spreadsheet in order to perform a new assessment with different risk events

## Rating tables
In this sheet, you can "design" you risk matrix to your needs. Or you can use or pre-defined options and go the the next sheet directly
Default construction
For rating tables: In order to begin with the tool, we propose to use the following values in yellow boxes: for damages 4/10/1000 and for likelihood 4/10/0,0001. This will lead to use 4 rating levels for each scale. The qualitative comment in boxes "i22:i26" may be used by participants instead of likelihood quantified values. This may facilitate the scoring | [8 empty] | For acceptability thresholds, you have two choices i, the drop-down list: - use default construction of the threshold matrix: the sum of likelihood level + damage level is compared with the first and second thresholds that you can choose below - use your own rating table: in this case complete the matrix with 1 (acceptable), 2 (Moderate risk), 3 (Unacceptable risk) | [5 empty] | Your own rating table
For a more advanced use of the tool, you can create up to 10 levels and change values indicated in yellow boxes. It should be noted that for proper use of the tool, "multiplicative factors" should be kept close for damages and likelihood. Indeed, in the "risk assessment" sheet, the risk is estimated by summing damage level and "likelihood level", which is relevant for logarithmic scales, as proposed here. It is demonstrated below that if you respect this, the value obtained for risk assessment is proportional to the sum of damage level and likelihood level. Risk = Likelihood x Damage Log(Risk) = log(Likelihood x Damage) = log(Likelihood) + log(Damage) dl_d ~ mf_d ^ dl_d and dl_l ~ mf_l ^ dl_l Log(Risk) ~ log(mf_d ^ dl_d) + log(mf_l ^ dl_l)~ dl_d x log(mf_d) + dl_l x log(mf_l) If mf_d = mf_l = mf : Risk Index (RI) ~ Log(Risk) ~ (dl_d+ dl_l) x log(mf) ~dl_d+ dl_l Notations: dl: damage level / mf:multiplicative factor / _d : damages / _l : likelihood
Choose your matrix construction:
[9 empty] | Risk matrix |  |  |  |  | Your own rating table
Create your rating table for damages |  |  |  | Create your rating table for likelihood |  |  |  |  | Acceptability thresholds
Number of damage levels |  | 4 |  | Number of likelihood levels |  | 4 |  |  | 1st |  |  |  |  | 5
Multiplicative factor |  | 10 |  | Multiplicative factor |  | 10 |  |  | 2nd |  |  |  |  | 8
Minimum value |  | 1000 |  | Minimum value |  | 0.0001 |  |  |  | Damages
Maximum value |  | 1000000 |  | Maximum value |  | 0.1 |  |  |  | 1 | 2 | 3 | 4
[8 empty] | Likelihood | 1 | 2 | 3 | 4 | 5
Damage rating table |  |  |  | Likelihood rating table |  |  |  |  | 2 | 3 | 4 | 5 | 6
Damage level | The damage level is comprised between: |  |  | Likelihood level | The damage level is comprised between: |  |  |  | 3 | 4 | 5 | 6 | 7
| Minimum value | Maximum value |  |  | Minimum value | Maximum value |  |  | 4 | 5 | 6 | 7 | 8
1 | 0 | 1000 | Very low damage | 1 | 0 | 0.0001 | Not likely to occur
2 | 1000 | 10000 | Low damage | 2 | 0.0001 | 0.001 | Mild chance of occurence
3 | 10000 | 100000 | Medium damage | 3 | 0.001 | 0.01 | Moderate chance of occurence
4 | 100000 | 1000000 | High damage | 4 | 0.01 | 0.1 | High chances of occurence
Damages
[10 empty] | 1 | 2 | 3 | 4
[8 empty] | Likelihood | 1 | 1 | 1 | 1 | 2
[9 empty] | 2 | 1 | 1 | 2 | 2
[9 empty] | 3 | 1 | 2 | 2 | 3
[9 empty] | 4 | 2 | 2 | 3 | 3
Change the qualitative description to your needs
Change the qualitative description to your needs
For probabilities, check that the maximum value is below 1, otherwise it is a frequency

## Feuil2 (hidden)
Damage | Likelihood | Like-Dam | Like+Dam | Default | My own rating table | total
1 | 1 | 1-1 | 2 | 1 | 1 | 1
2 | 1 | 1-2 | 3 | 1 | 1 | 1
3 | 1 | 1-3 | 4 | 1 | 1 | 1
4 | 1 | 1-4 | 5 | 2 | 2 | 2
1 | 2 | 2-1 | 3 | 1 | 1 | 1
2 | 2 | 2-2 | 4 | 1 | 1 | 1
3 | 2 | 2-3 | 5 | 2 | 2 | 2
4 | 2 | 2-4 | 6 | 2 | 2 | 2
1 | 3 | 3-1 | 4 | 1 | 1 | 1
2 | 3 | 3-2 | 5 | 2 | 2 | 2
3 | 3 | 3-3 | 6 | 2 | 2 | 2
4 | 3 | 3-4 | 7 | 2 | 3 | 3
1 | 4 | 4-1 | 5 | 2 | 2 | 2
2 | 4 | 4-2 | 6 | 2 | 2 | 2
3 | 4 | 4-3 | 7 | 2 | 3 | 3
4 | 4 | 4-4 | 8 | 3 | 3 | 3
1
2
3
4
1
2
3
4
1
2
3
4
1
2
3
4
1
2
3
4
1
2
3
4
1
2
3
4
1
2
3
4
1
2
3
4
1
2
3
4
1
2
3
4
1
2
3
4
1
2
3
4
1
2
3
4
1
2
3
4
1
2
3
4
1
2
3
4
1
2
3
4
1
2
3
4
1
2
3
4
1
2
3
4

## Risk assessment
| In order to perform the risk assessment, you are invited to complete the likelihood and damage levels for each selected risk. Th Risk index (RI) will then be computed, with an interpretation in terms of acceptabilty, following the thresholds you define in the sheet "Rating table". This speadsheet can be used for a second assessment, for instance after application of de-risking or mitigation (columns I and J). Evolution between both versions are highlighted in grey. In column N, you will find for each selected risk a link to the Georisk online tool with information on risks and on means to prevent or mitigate it. This may be helpful to tackle high and unacceptable risks, and to reduce risks. | [7 empty] | Number of risks considered
[7 empty] | Managerial and Socio-economic |  | 16
| 1 | These risks are considered acceptable |  |  |  |  | Operation and Geology |  | 21
| 2 | Moderate to high risks: you should consider additional mitigation measures where practical |  |  |  |  | Drilling |  | 17
| 23 | Unacceptable risks. You need to consider additional de-risking or mitigation measures |  |  |  |  | New risks |  | 3 | 57
|  |  | First assessment |  | 2021-01-01 |  |  |  | Re-assessment |  | 2021-01-01
| ID | Description | Likelihood | Damage Level | RI |  | Comments |  | Likelihood | Damage Level | RI | Link | Comments on de-risking and mitigation
1 | A-1 | External natural hazards damaging the infrastructure | 1 | 1 | 2 | 1 |  | TRUE |  |  | 0 | (Info) |  | 1-1 | 1 | 1-1-1 | #N/A | #N/A | #N/A | #N/A
2 | A-2 | Anthropogenic hazard damaging the infrastructure | 1 | 1 | 2 | 1 |  | TRUE |  |  | 0 | (Info) |  | 1-1 | 2 | 1-1-2 | #N/A | #N/A | #N/A | #N/A
3 | B-1 | Changes in policies, laws, taxes and regulations put development/economy in jeopardy | 1 | 1 | 2 | 1 |  | TRUE |  |  | 0 | (Info) |  | 1-1 | 3 | 1-1-3 | #N/A | #N/A | #N/A | #N/A
4 | B-2 | Lack of financing for the next phases | 1 | 1 | 2 | 1 |  | TRUE |  |  | 0 | (Info) |  | 1-1 | 4 | 1-1-4 | #N/A | #N/A | #N/A | #N/A
5 | B-3 | Low social acceptance put barrier to development | 1 | 1 | 2 | 1 |  | TRUE |  |  | 0 | (Info) |  | 1-1 | 5 | 1-1-5 | #N/A | #N/A | #N/A | #N/A
6 | B-4 | Public opposition against nuisances from the exploitation | 1 | 1 | 2 | 1 |  | TRUE |  |  | 0 | (Info) |  | 1-1 | 6 | 1-1-6 | #N/A | #N/A | #N/A | #N/A
7 | B-6 | Lack or loss of clients | 1 | 1 | 2 | 1 |  | TRUE |  |  | 0 | (Info) |  | 1-1 | 7 | 1-1-7 | #N/A | #N/A | #N/A | #N/A
8 | B-8 | Significant changes of energy costs | 1 | 1 | 2 | 1 |  | TRUE |  |  | 0 | (Info) |  | 1-1 | 8 | 1-1-8 | #N/A | #N/A | #N/A | #N/A
9 | C-1 | Low financing for work leading to low safety standards | 1 | 1 | 2 | 1 |  | TRUE |  |  | 0 | (Info) |  | 1-1 | 9 | 1-1-9 | #N/A | #N/A | #N/A | #N/A
10 | B-5 | Unanticipated delays and costs in operations (materials, services, maintenance) | 1 | 1 | 2 | 1 |  | TRUE |  |  | 0 | (Info) |  | 1-1 | 10 | 1-1-10 | #N/A | #N/A | #N/A | #N/A
11 | C-2 | Suboptimal design of well leads to reduced flow rate | 1 | 1 | 2 | 1 |  | TRUE |  |  | 0 | (Info) |  | 1-1 | 11 | 1-1-11 | #N/A | #N/A | #N/A | #N/A
12 | C-3 | Best practices not applied (data acquisition, modelling, decision making, design of wells / plants, construction) | 1 | 1 | 2 | 1 |  | TRUE |  |  | 0 | (Info) |  | 1-1 | 12 | 1-1-12 | #N/A | #N/A | #N/A | #N/A
13 | C-4 | Unsuitable contracts (roles and responsibility not clearly defined) leading to suboptimal performance or exploding costs | 1 | 1 | 2 | 1 |  | TRUE |  |  | 0 | (Info) |  | 1-1 | 13 | 1-1-13 | #N/A | #N/A | #N/A | #N/A
14 | C-8 | Organization is not experienced / financially robust enough for the challenge | 1 | 1 | 2 | 1 |  | TRUE |  |  | 0 | (Info) |  | 1-1 | 14 | 1-1-14 | #N/A | #N/A | #N/A | #N/A
15 | B-9 | The research or exploitation permit is changed in favor of another resource | 1 | 1 | 2 | 1 |  | TRUE |  |  | 0 | (Info) |  | 1-1 | 15 | 1-1-15 | #N/A | #N/A | #N/A | #N/A
16 | C-9 | Demand analysis and forecast are inaccurate | 1 | 1 | 2 | 1 |  | TRUE |  |  | 0 | (Info) |  | 1-1 | 16 | 1-1-16 | #N/A | #N/A | #N/A | #N/A
17 | D-1 | Flow rate lower than expected (reservoir) | 1 | 1 | 2 | 1 |  | TRUE |  |  | 0 | (Info) |  | 1-1 | 17 | 1-1-17 | #N/A | #N/A | #N/A | #N/A
18 | D-2 | Flow rate degrades over time | 1 | 1 | 2 | 1 |  | TRUE |  |  | 0 | (Info) |  | 1-1 | 18 | 1-1-18 | #N/A | #N/A | #N/A | #N/A
19 | D-3 | Temperature lower than expected (reservoir) | 1 | 1 | 2 | 1 |  | TRUE |  |  | 0 | (Info) |  | 1-1 | 19 | 1-1-19 | #N/A | #N/A | #N/A | #N/A
20 | D-4 | Temperature degrades too quickly | 1 | 1 | 2 | 1 |  | TRUE |  |  | 0 | (Info) |  | 1-1 | 20 | 1-1-20 | #N/A | #N/A | #N/A | #N/A
21 | D-5 | Pressure lower/higher than expected | 1 | 1 | 2 | 1 |  | TRUE |  |  | 0 | (Info) |  | 1-1 | 21 | 1-1-21 | #N/A | #N/A | #N/A | #N/A
22 | D-6 | Pressure is changing during the operation in an unexpected way | 1 | 1 | 2 | 1 |  | TRUE |  |  | 0 | (Info) |  | 1-1 | 22 | 1-1-22 | #N/A | #N/A | #N/A | #N/A
23 | B-7 | Neighbouring operators cause negative changes to the reservoir parameters. | 1 | 1 | 2 | 1 |  | TRUE |  |  | 0 | (Info) |  | 1-1 | 23 | 1-1-23 | #N/A | #N/A | #N/A | #N/A
24 | D-7 | Fluid chemistry/ gas content / physical properties are different from expected | 1 | 1 | 2 | 1 |  | TRUE |  |  | 0 | (Info) |  | 1-1 | 24 | 1-1-24 | #N/A | #N/A | #N/A | #N/A
25 | F-6 | NCG Production | 1 | 1 | 2 | 1 |  | TRUE |  |  | 0 | (Info) |  | 1-1 | 25 | 1-1-25 | #N/A | #N/A | #N/A | #N/A
26 | C-5-a | Human error leading to failure during work (including either insufficient background and/or regulations) [Op&Geology] | 1 | 1 | 2 | 1 |  | TRUE |  |  | 0 | (Info) |  | 1-1 | 26 | 1-1-26 | #N/A | #N/A | #N/A | #N/A
27 | D-8 | Fluid chemistry/ gas content / physical properties change | 1 | 1 | 2 | 1 |  | TRUE |  |  | 0 | (Info) |  | 1-1 | 27 | 1-1-27 | #N/A | #N/A | #N/A | #N/A
28 | D-9 | Target formation is missing in the well (unexpected geology, insufficient exploration) | 1 | 1 | 2 | 1 |  | TRUE |  |  | 0 | (Info) |  | 1-1 | 28 | 1-1-28 | #N/A | #N/A | #N/A | #N/A
29 | D-10 | Target formation has no/insufficient fluid for commercial production | 1 | 1 | 2 | 1 |  | TRUE |  |  | 0 | (Info) |  | 1-1 | 29 | 1-1-29 | #N/A | #N/A | #N/A | #N/A
30 | D-11 | Geological lithology or stratigraphy is different than expected | 1 | 1 | 2 | 1 |  | TRUE |  |  | 0 | (Info) |  | 1-1 | 30 | 1-1-30 | #N/A | #N/A | #N/A | #N/A
31 | D-12 | Excessive scaling in the geothermal loop | 1 | 1 | 2 | 1 |  | TRUE |  |  | 0 | (Info) |  | 1-1 | 31 | 1-1-31 | #N/A | #N/A | #N/A | #N/A
32 | D-13 | Excessive corrosion in the geothermal loop | 1 | 1 | 2 | 1 |  | TRUE |  |  | 0 | (Info) |  | 1-1 | 32 | 1-1-32 | #N/A | #N/A | #N/A | #N/A
33 | D-14 | Particle production ("sanding") | 1 | 1 | 2 | 1 |  | TRUE |  |  | 0 | (Info) |  | 1-1 | 33 | 1-1-33 | #N/A | #N/A | #N/A | #N/A
34 | D-15 | Hydraulic connectivity between wells is insufficient for commercial use | 1 | 1 | 2 | 1 |  | TRUE |  |  | 0 | (Info) |  | 1-1 | 34 | 1-1-34 | #N/A | #N/A | #N/A | #N/A
35 | D-16 | Re-injection of the fluid is more difficult than expected | 1 | 1 | 2 | 1 |  | TRUE |  |  | 0 | (Info) |  | 1-1 | 35 | 1-1-35 | #N/A | #N/A | #N/A | #N/A
36 | D-17 | Degradation of the reservoir (structure, properties, deteriorating whole-scale further commercial utilization) | 1 | 1 | 2 | 1 |  | TRUE |  |  | 0 | (Info) |  | 1-1 | 36 | 1-1-36 | #N/A | #N/A | #N/A | #N/A
37 | F-8-a | Loss of integrity of surface equipments (leakage from the tanks, pipeline, heat-exchanger, etc.) [Operation&Geology] | 1 | 1 | 2 | 1 |  | TRUE |  |  | 0 | (Info) |  | 1-1 | 37 | 1-1-37 | #N/A | #N/A | #N/A | #N/A
38 | E-1 | Fluid losses leading to severe technical issues | 1 | 1 | 2 | 1 |  | TRUE |  |  | 0 | (Info) |  | 1-1 | 38 | 1-1-38 | #N/A | #N/A | #N/A | #N/A
39 | C-7 | Damage to the well/reservoir while drilling or testing | 1 | 1 | 2 | 1 |  | TRUE |  |  | 0 | (Info) |  | 1-1 | 39 | 1-1-39 | #N/A | #N/A | #N/A | #N/A
40 | E-2 | Wellbore instability | 1 | 1 | 2 | 1 |  | TRUE |  |  | 0 | (Info) |  | 1-1 | 40 | 1-1-40 | #N/A | #N/A | #N/A | #N/A
41 | E-3 | Trajectory issues (deviation from target) | 1 | 1 | 2 | 1 |  | TRUE |  |  | 0 | (Info) |  | 1-1 | 41 | 1-1-41 | #N/A | #N/A | #N/A | #N/A
42 | F-8-b | Loss of integrity of surface equipments (leakage from the mud mud pit; well head and etc.) [Drilling] | 1 | 1 | 2 | 1 |  | TRUE |  |  | 0 | (Info) |  | 1-1 | 42 | 1-1-42 | #N/A | #N/A | #N/A | #N/A
43 | F-7 | Loss of integrity of the wellbore (connection of well fluid with surface; inter layer fluid connection; etc.) | 1 | 1 | 2 | 1 |  | TRUE |  |  | 0 | (Info) |  | 1-1 | 43 | 1-1-43 | #N/A | #N/A | #N/A | #N/A
44 | C-6 | Wrong choice of stimulation fluids or techniques damaging the reservoir/well | 1 | 1 | 2 | 1 |  | TRUE |  |  | 0 | (Info) |  | 1-1 | 44 | 1-1-44 | #N/A | #N/A | #N/A | #N/A
45 | E-7 | Issues in transporting/handling radioactive sources for logging | 1 | 1 | 2 | 1 |  | TRUE |  |  | 0 | (Info) |  | 1-1 | 45 | 1-1-45 | #N/A | #N/A | #N/A | #N/A
46 | E-8 | Technical failure of the equipment | 1 | 1 | 2 | 1 |  | TRUE |  |  | 0 | (Info) |  | 1-1 | 46 | 1-1-46 | #N/A | #N/A | #N/A | #N/A
47 | E-9 | Well casing collapse | 1 | 1 | 2 | 1 |  | TRUE |  |  | 0 | (Info) |  | 1-1 | 47 | 1-1-47 | #N/A | #N/A | #N/A | #N/A
48 | F-1 | Blowouts | 1 | 1 | 2 | 1 |  | TRUE |  |  | 0 | (Info) |  | 1-1 | 48 | 1-1-48 | #N/A | #N/A | #N/A | #N/A
49 | F-2 | Fluid communication between different formations due to ineffective isolation of the well | 1 | 1 | 2 | 1 |  | TRUE |  |  | 0 | (Info) |  | 1-1 | 49 | 1-1-49 | #N/A | #N/A | #N/A | #N/A
50 | F-3 | Induced seismicity (above sensitivity level) | 1 | 1 | 2 | 1 |  | TRUE |  |  | 0 | (Info) |  | 1-1 | 50 | 1-1-50 | #N/A | #N/A | #N/A | #N/A
51 | F-4 | Surface subsidence or uplift | 1 | 1 | 2 | 1 |  | TRUE |  |  | 0 | (Info) |  | 1-1 | 51 | 1-1-51 | #N/A | #N/A | #N/A | #N/A
52 | F-5 | Toxic emissions due to gases and fluids produced in-situ | 1 | 1 | 2 | 1 |  | TRUE |  |  | 0 | (Info) |  | 1-1 | 52 | 1-1-52 | #N/A | #N/A | #N/A | #N/A
53 | C-5-b | Human error leading to failure during work (including either insufficient background and/or safety regulations) [Drilling] | 1 | 1 | 2 | 1 |  | TRUE |  |  | 0 | (Info) |  | 1-1 | 53 | 1-1-53 | #N/A | #N/A | #N/A | #N/A
54 | E-5 | Technical failure/difficulties during drilling (due to any additional causes that were not mentioned) | 1 | 1 | 2 | 1 |  | TRUE |  |  | 0 | (Info) |  | 1-1 | 54 | 1-1-54 | #N/A | #N/A | #N/A | #N/A
55 | N-1 | My new risk | 1 | 1 | 2 | 1 |  | TRUE |  |  | 0 |  |  | 1-1 | 55 | 1-1-55 | #N/A | #N/A | #N/A | #N/A
56 | N-2 | My new risk 2 | 1 | 1 | 2 | 1 |  | TRUE |  |  | 0 |  |  | 1-1 | 56 | 1-1-56 | #N/A | #N/A | #N/A | #N/A
57 | N-3 | My new risk 3 | 1 | 1 | 2 | 1 |  | TRUE |  |  | 0 |  |  | 1-1 | 57 | 1-1-57 | #N/A | #N/A | #N/A | #N/A
58 | [7 empty] | FALSE | [8 empty] | #N/A | #N/A | #N/A | #N/A
59 | [7 empty] | FALSE | [8 empty] | #N/A | #N/A | #N/A | #N/A
60 | [7 empty] | FALSE | [8 empty] | #N/A | #N/A | #N/A | #N/A
61 | [7 empty] | FALSE | [8 empty] | #N/A | #N/A | #N/A | #N/A
62 | [7 empty] | FALSE | [8 empty] | #N/A | #N/A | #N/A | #N/A
63 | [7 empty] | FALSE | [8 empty] | #N/A | #N/A | #N/A | #N/A
64 | [7 empty] | FALSE | [8 empty] | #N/A | #N/A | #N/A | #N/A
65 | [7 empty] | FALSE | [8 empty] | #N/A | #N/A | #N/A | #N/A
66 | [7 empty] | FALSE | [8 empty] | #N/A | #N/A | #N/A | #N/A
67 | [7 empty] | FALSE | [8 empty] | #N/A | #N/A | #N/A | #N/A
68 | [7 empty] | FALSE | [8 empty] | #N/A | #N/A | #N/A | #N/A
69 | [7 empty] | FALSE | [8 empty] | #N/A | #N/A | #N/A | #N/A
70 | [7 empty] | FALSE | [8 empty] | #N/A | #N/A | #N/A | #N/A
71 | [7 empty] | FALSE | [8 empty] | #N/A | #N/A | #N/A | #N/A
72 | [7 empty] | FALSE | [8 empty] | #N/A | #N/A | #N/A | #N/A
73 | [7 empty] | FALSE | [8 empty] | #N/A | #N/A | #N/A | #N/A
74 | [7 empty] | FALSE | [8 empty] | #N/A | #N/A | #N/A | #N/A
75 | [7 empty] | FALSE | [8 empty] | #N/A | #N/A | #N/A | #N/A
76 | [7 empty] | FALSE | [8 empty] | #N/A | #N/A | #N/A | #N/A
77 | [7 empty] | FALSE | [8 empty] | #N/A | #N/A | #N/A | #N/A
78 | [7 empty] | FALSE | [8 empty] | #N/A | #N/A | #N/A | #N/A
79 | [7 empty] | FALSE | [8 empty] | #N/A | #N/A | #N/A | #N/A
80 | [7 empty] | FALSE | [8 empty] | #N/A | #N/A | #N/A | #N/A
81 | [7 empty] | FALSE | [8 empty] | #N/A | #N/A | #N/A | #N/A
82 | [7 empty] | FALSE | [8 empty] | #N/A | #N/A | #N/A | #N/A
83 | [7 empty] | FALSE | [8 empty] | #N/A | #N/A | #N/A | #N/A
84 | [7 empty] | FALSE | [8 empty] | #N/A | #N/A | #N/A | #N/A
85 | [7 empty] | FALSE | [8 empty] | #N/A | #N/A | #N/A | #N/A
86 | [7 empty] | FALSE | [8 empty] | #N/A | #N/A | #N/A | #N/A
87 | [7 empty] | FALSE | [8 empty] | #N/A | #N/A | #N/A | #N/A
88 | [7 empty] | FALSE | [8 empty] | #N/A | #N/A | #N/A | #N/A
89 | [7 empty] | FALSE | [8 empty] | #N/A | #N/A | #N/A | #N/A
90 | [7 empty] | FALSE | [8 empty] | #N/A | #N/A | #N/A | #N/A
91 | [7 empty] | FALSE | [8 empty] | #N/A | #N/A | #N/A | #N/A
92 | [7 empty] | FALSE | [8 empty] | #N/A | #N/A | #N/A | #N/A
93 | [7 empty] | FALSE | [8 empty] | #N/A | #N/A | #N/A | #N/A
94 | [7 empty] | FALSE | [8 empty] | #N/A | #N/A | #N/A | #N/A
95 | [7 empty] | FALSE | [8 empty] | #N/A | #N/A | #N/A | #N/A
96 | [7 empty] | FALSE | [8 empty] | #N/A | #N/A | #N/A | #N/A
97 | [7 empty] | FALSE | [8 empty] | #N/A | #N/A | #N/A | #N/A
98 | [7 empty] | FALSE | [8 empty] | #N/A | #N/A | #N/A | #N/A
99 | [7 empty] | FALSE | [8 empty] | #N/A | #N/A | #N/A | #N/A
100 | [7 empty] | FALSE | [8 empty] | #N/A | #N/A | #N/A | #N/A
101 | [7 empty] | FALSE | [8 empty] | #N/A | #N/A | #N/A | #N/A
102 | [7 empty] | FALSE | [8 empty] | #N/A | #N/A | #N/A | #N/A
103 | [7 empty] | FALSE | [8 empty] | #N/A | #N/A | #N/A | #N/A
104 | [7 empty] | FALSE | [8 empty] | #N/A | #N/A | #N/A | #N/A
105 | [7 empty] | FALSE | [8 empty] | #N/A | #N/A | #N/A | #N/A
106 | [7 empty] | FALSE | [8 empty] | #N/A | #N/A | #N/A | #N/A
107 | [7 empty] | FALSE | [8 empty] | #N/A | #N/A | #N/A | #N/A
159 | [7 empty] | FALSE | [8 empty] | #N/A | #N/A | #N/A | #N/A
160 | [7 empty] | FALSE | [8 empty] | #N/A | #N/A | #N/A | #N/A
161 | [7 empty] | FALSE | [8 empty] | #N/A | #N/A | #N/A | #N/A
162 | [7 empty] | FALSE | [8 empty] | #N/A | #N/A | #N/A | #N/A
163 | [7 empty] | FALSE | [8 empty] | #N/A | #N/A | #N/A | #N/A
164 | [7 empty] | FALSE | [8 empty] | #N/A | #N/A | #N/A | #N/A
165 | [7 empty] | FALSE | [8 empty] | #N/A | #N/A | #N/A | #N/A
166 | [7 empty] | FALSE | [8 empty] | #N/A | #N/A | #N/A | #N/A
167 | [7 empty] | FALSE | [8 empty] | #N/A | #N/A | #N/A | #N/A
168 | [7 empty] | FALSE | [8 empty] | #N/A | #N/A | #N/A | #N/A
169 | [7 empty] | FALSE | [8 empty] | #N/A | #N/A | #N/A | #N/A
170 | [7 empty] | FALSE | [8 empty] | #N/A | #N/A | #N/A | #N/A
171 | [7 empty] | FALSE | [8 empty] | #N/A | #N/A | #N/A | #N/A
172 | [7 empty] | FALSE | [8 empty] | #N/A | #N/A | #N/A | #N/A
173 | [7 empty] | FALSE | [8 empty] | #N/A | #N/A | #N/A | #N/A
174 | [7 empty] | FALSE | [8 empty] | #N/A | #N/A | #N/A | #N/A
175 | [7 empty] | FALSE | [8 empty] | #N/A | #N/A | #N/A | #N/A
176 | [7 empty] | FALSE | [8 empty] | #N/A | #N/A | #N/A | #N/A
177 | [7 empty] | FALSE | [8 empty] | #N/A | #N/A | #N/A | #N/A
178 | [7 empty] | FALSE | [8 empty] | #N/A | #N/A | #N/A | #N/A
179 | [7 empty] | FALSE | [8 empty] | #N/A | #N/A | #N/A | #N/A

## Plots
These figures plot the results for first assessment.
Risk Index | Number of occurrences | Acceptability | Number of occurrences
2 | 57 | 1 | 57
3 | 0 | 2 | 0
4 | 0 | 3 | 0
5 | 0
6 | 0
7 | 0
8 | 0

## Re-assessment plots
These figures plot the results for first assessment.
Risk Index | Number of occurrences | Acceptability | Number of occurrences
2 | 0 | 1 | 0
3 | 0 | 2 | 0
4 | 0 | 3 | 0
5 | 0
6 | 0
7 | 0
8 | 0

## PlotMatrix_dots
In this sheet, you can choose up to 12 risks that can be represented in a matrix. At the top, the risks are mapped at their exact place, with size of points representative of the risk index (likelihood+damage level). It may be unpracticable for same quotations. A second map at the bottom, with smaller points, is proposed. Points are randomly moved from a value comprised between 0 and -0,2, so that all points are made visible. White points correspond to re-assessment.
[8 empty] | 1 | 0.4
Choose the risks that you want to plot on the matrix: |  |  | Likelihood | Damage level |  | Likelihood | Damage level |  | Likelihood | Damage level | Likelihood | Damage level
| N-2 | My new risk 2 | 1 | 1 | 2 |  |  |  | 0.73 | 0.64 |  |  | 0 | 1
| N-3 | My new risk 3 | 1 | 1 | 2 |  |  |  | 0.83 | 0.84 |  |  | 0 | 1
[13 empty] | 0 | 0
[13 empty] | 0 | 0
[13 empty] | 0 | 0
[13 empty] | 0 | 0
[13 empty] | 0 | 0
[13 empty] | 0 | 0
[13 empty] | 0 | 0
[13 empty] | 0 | 0
[13 empty] | 0 | 0
[13 empty] | 0 | 0

## Feuil1 (hidden)
Damage | Likelihood |  |  |  | 57 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63 | 64 | 65 | 66 | 67 | 68 | 69 | 70 | 71 | 72 | 73 | 74 | 75 | 76 | 77 | 78 | 79 | 80 | 81 | 82 | 83 | 84 | 85 | 86 | 87 | 88 | 89 | 90 | 91 | 92 | 93 | 94 | 95 | 96 | 97 | 98 | 99 | 100
1 | 1 | 1-1 | A-1 ;A-2 ;B-1 ;B-2 ;B-3 ;B-4 ;B-6 ;B-8 ;C-1 ;B-5 ;C-2 ;C-3 ;C-4 ;C-8 ;B-9 ;C-9 ;D-1 ;D-2 ;D-3 ;D-4 ;D-5 ;D-6 ;B-7 ;D-7 ;F-6 ;C-5-a ;D-8 ;D-9 ;D-10 ;D-11 ; | A-1 ;A-2 ;B-1 ;B-2 ;B-3 ;B-4 ;B-6 ;B-8 ;C-1 ;B-5 ;C-2 ;C-3 ;C-4 ;C-8 ;B-9 ;C-9 ;D-1 ;D-2 ;D-3 ;D-4 ;D-5 ;D-6 ;B-7 ;D-7 ;F-6 ;C-5-a ;D-8 ;D-9 ;D-10 ;D-11 | 57: 57; 1: A-1 ;; 2: A-2 ;; 3: B-1 ;; 4: B-2 ;; 5: B-3 ;; 6: B-4 ;; 7: B-6 ;; 8: B-8 ;; 9: C-1 ;; 10: B-5 ;; 11: C-2 ;; 12: C-3 ;; 13: C-4 ;; 14: C-8 ;; 15: B-9 ;; 16: C-9 ;; 17: D-1 ;; 18: D-2 ;; 19: D-3 ;; 20: D-4 ;; 21: D-5 ;; 22: D-6 ;; 23: B-7 ;; 24: D-7 ;; 25: F-6 ;; 26: C-5-a ;; 27: D-8 ;; 28: D-9 ;; 29: D-10 ;; 30: D-11 ;; 31: D-12 ;; 32: D-13 ;; 33: D-14 ;; 34: D-15 ;; 35: D-16 ;; 36: D-17 ;; 37: F-8-a ;; 38: E-1 ;; 39: C-7 ;; 40: E-2 ;; 41: E-3 ;; 42: F-8-b ;; 43: F-7 ;; 44: C-6 ;; 45: E-7 ;; 46: E-8 ;; 47: E-9 ;; 48: F-1 ;; 49: F-2 ;; 50: F-3 ;; 51: F-4 ;; 52: F-5 ;; 53: C-5-b ;; 54: E-5 ;; 55: N-1 ;; 56: N-2 ;; 57: N-3 ;
2 | 1 | 2-1 |  |  | 57: 0
3 | 1 | 3-1 |  |  | 57: 0
4 | 1 | 4-1 |  |  | 57: 0
1 | 2 | 1-2 |  |  | 57: 0
2 | 2 | 2-2 |  |  | 57: 0
3 | 2 | 3-2 |  |  | 57: 0
4 | 2 | 4-2 |  |  | 57: 0
1 | 3 | 1-3 |  |  | 57: 0
2 | 3 | 2-3 |  |  | 57: 0
3 | 3 | 3-3 |  |  | 57: 0
4 | 3 | 4-3 |  |  | 57: 0
1 | 4 | 1-4 |  |  | 57: 0
2 | 4 | 2-4 |  |  | 57: 0
3 | 4 | 3-4 |  |  | 57: 0
4 | 4 | 4-4 |  |  | 57: 0
1 |  |  |  |  | 57: 0
2 |  |  |  |  | 57: 0
3 |  |  |  |  | 57: 0
4 |  |  |  |  | 57: 0
1 |  |  |  |  | 57: 0
2 |  |  |  |  | 57: 0
3 |  |  |  |  | 57: 0
4 |  |  |  |  | 57: 0
1 |  |  |  |  | 57: 0
2 |  |  |  |  | 57: 0
3 |  |  |  |  | 57: 0
4 |  |  |  |  | 57: 0
1 |  |  |  |  | 57: 0
2 |  |  |  |  | 57: 0
3 |  |  |  |  | 57: 0
4 |  |  |  |  | 57: 0
1 |  |  |  |  | 57: 0
2 |  |  |  |  | 57: 0
3 |  |  |  |  | 57: 0
4 |  |  |  |  | 57: 0
1 |  |  |  |  | 57: 0
2 |  |  |  |  | 57: 0
3 |  |  |  |  | 57: 0
4 |  |  |  |  | 57: 0
1 |  |  |  |  | 57: 0
2 |  |  |  |  | 57: 0
3 |  |  |  |  | 57: 0
4 |  |  |  |  | 57: 0
1 |  |  |  |  | 57: 0
2 |  |  |  |  | 57: 0
3 |  |  |  |  | 57: 0
4 |  |  |  |  | 57: 0
1 |  |  |  |  | 57: 0
2 |  |  |  |  | 57: 0
3 |  |  |  |  | 57: 0
4 |  |  |  |  | 57: 0
1 |  |  |  |  | 57: 0
2 |  |  |  |  | 57: 0
3 |  |  |  |  | 57: 0
4 |  |  |  |  | 57: 0
1 |  |  |  |  | 57: 0
2 |  |  |  |  | 57: 0
3 |  |  |  |  | 57: 0
4 |  |  |  |  | 57: 0
1 |  |  |  |  | 57: 0
2 |  |  |  |  | 57: 0
3 |  |  |  |  | 57: 0
4 |  |  |  |  | 57: 0
1 |  |  |  |  | 57: 0
2 |  |  |  |  | 57: 0
3 |  |  |  |  | 57: 0
4 |  |  |  |  | 57: 0
1 |  |  |  |  | 57: 0
2 |  |  |  |  | 57: 0
3 |  |  |  |  | 57: 0
4 |  |  |  |  | 57: 0
1 |  |  |  |  | 57: 0
2 |  |  |  |  | 57: 0
3 |  |  |  |  | 57: 0
4 |  |  |  |  | 57: 0
1 |  |  |  |  | 57: 0
2 |  |  |  |  | 57: 0
3 |  |  |  |  | 57: 0
4 |  |  |  |  | 57: 0
1 |  |  |  |  | 57: 0
2 |  |  |  |  | 57: 0
3 |  |  |  |  | 57: 0
4 |  |  |  |  | 57: 0
1 |  |  |  |  | 57: 0
2 |  |  |  |  | 57: 0
3 |  |  |  |  | 57: 0
4 |  |  |  |  | 57: 0
1 |  |  |  |  | 57: 0
2 |  |  |  |  | 57: 0
3 |  |  |  |  | 57: 0
4 |  |  |  |  | 57: 0
1 |  |  |  |  | 57: 0
2 |  |  |  |  | 57: 0
3 |  |  |  |  | 57: 0
4 |  |  |  |  | 57: 0
1 |  |  |  |  | 57: 0
2 |  |  |  |  | 57: 0
3 |  |  |  |  | 57: 0
4 |  |  |  |  | 57: 0
1 |  |  |  |  | 57: 0
2 |  |  |  |  | 57: 0
3 |  |  |  |  | 57: 0
4 |  |  |  |  | 57: 0

## PlotMatrix_Heat
Risk Matrix
LIKELIHOOD | 4
3
2
| 1 | A-1 ;A-2 ;B-1 ;B-2 ;B-3 ;B-4 ;B-6 ;B-8 ;C-1 ;B-5 ;C-2 ;C-3 ;C-4 ;C-8 ;B-9 ;C-9 ;D-1 ;D-2 ;D-3 ;D-4 ;D-5 ;D-6 ;B-7 ;D-7 ;F-6 ;C-5-a ;D-8 ;D-9 ;D-10 ;D-11
| 0 | 1 | 2 | 3 | 4
DAMAGE
|  | 2 | 2 | 3 | 3
|  | 1 | 2 | 2 | 3
|  | 1 | 1 | 2 | 2
|  | 1 | 1 | 1 | 2

## Help
Project Information
At the top of the the Risk identification sheet, you can find several cells that allow you to specify basic information regarding the assessment. - Date: you can specify the date of the assessment - Name of project: you can specify a name for the project that is being assessed - version of assessment: you can use this cell for version numbering, which can be useful for keeping track of the evolution of the risks in case of subsequent updates - additional details: put here any information that can be useful to remember in relation to this specific assessment You are also welcome to add new rows if you need to put more information
Risk categories
The current list of risk is classified according to three categories: managerial and social-economic, operation and geology, and drilling. These categories were chosen corresponding to typical profiles of experts. They are then used for grouping the risks into diagrams, for facilitating analysis. They are however only indicative and have no implication on the results.
Changing the list of risks
The first step in risk assessment is to adjust the list of risks considered to your project. In this spreadsheet you have by default the list of risk that was built during the H2020 GEORISK project. It has been validated and used by many stakeholders so we believe it is a good starting point. However, you are free to ignore some suggestions. In this case put a 0 in the corresponding line in the risk identification sheet and the risk will not appear in the assessment and plot sheets. If you want to add other risks to the list, you can use the "new risks" category at the bottom of the sheet. Simply add a description. You can also change the Id, (just making sure it is a new one). You can keep these new risks in the "new risk" category, or you can assign it to a previous category by using the drop-down menu. You can change the names of the categories by editing the table at the top of the risk assessment sheet. This spreadsheet is entirely unlocked so you are free to change anything. IMPORTANT: once you have done a first assessment, you should not change the list of risk or it will assign the scores to the wrong lists. If you need to change the list of risks between a first and a second assessment, we recommend to start a new spreadsheet, select the risks first and then fill the values (eventually with copy / paste)
Rating tables:
Each risk is characterized by two scores: a damage score and a likelihood score. The damage score is proportional to the potential loss, and is often expressed in euros (or other currency), but you can express it in any meaningful unit: days of delays, percentage of loss, etc. The only caveat is that the table is the same for all risks in one spreadsheet. The likelihood score can be either a probability (a number between 0 and 1), or a frequency (number of occurence per year). By default, the two scores are on 4-level scales. You can change it to better suit your need, and choose up to 10 levels. You can also have different scales for damage and likelihood. You can then adjust the equivalent values in the tables by adjusting the minimum value and the multiplicative factor. You have a field next to each table for a qualitative description of each scale. You can change the description in order to assist in choosing the correct score. You can also manually change the quantitative values in the table, you only have to be aware that by doing so, the risk index we automatically compute becomes less relevant (see below)
Risk index
Since we use a log-scale by default, our risk index is the sum of the likelihood score and damage score (see discussion in the rating tables sheet for more details). We cannot change this, but you can choose acceptability thresholds independantly of this index if necessary (see below).
Acceptability Thresholds
Depending on the assigned score, an icon in the risk assessment sheet will give a visual representation of the acceptability of the risk. A green icon means it is accceptable, a yellow icon is an indication that the risk should be further reduced, and a red icon that it is unaccepteble. By default the thresholds are expressed in terms of the Risk Index only: green is for a RI strictly inferior to the first threshold (4 by default); yellow for RI superior to the first threshold (included) and strictly inferior to the second threshold (7 by default); red is for RI superior to the second threshold (included). These thresholds can be changed according to your preferences by changing the values under "acceptability threshold" in the Rating tables sheet. You will see a little matrix in green, orange and red showing you the zones corresponding to the thresholds. In addition, we now propose to define personalized acceptability thresholds depending on both damage and likelihood. In order to do this, you need to change the option under "choose your matrix construction", and choose "your own rating table". A small matrix will appear where you need to define the zones yourself by indicating "1" for green, "2" for orange, and "3" for red (we only consider three zones). you can find guidelines for designing your matrix in the following reference: Baybutt, P. (2018). Guidelines for designing risk matrices. Process safety progress, 37(1), 49-55.
Risk assessment
In the risk assessment sheet, you have two tables: the one on the left corresponds to a first assessment, and the one on the right to a new assessment (or re-assessment). Both tables work in the same way, each line is a risk that you have selected in the risk identification sheet. You then need to assign a score for the damage and likelihood for each risk by using the dropdown list or typing the score directly. The risk index is automatically computed and an icon will appear corresponding to the acceptability thresholds you defined
Plots
There are two similar sheets: plots and re-assessment plots. On the first sheet you will find plots corresponding the the first assessment only, while on the second you will find the plots for the second assessments. There is one plot per category and two histogram tables (one by risk index, and one by acceptability zone). You can change the display of each plot if you want to display damage and likelihood separately without the risk index.
Matrix plots
There are two additional sheets with different plots. In the "plotmatrix_dots" sheet, you can select a few risks to be displayed on the risk matrix. For this, use the dropdown menu next to each color in the table. A "bubble" will appear in the matrix. If you re-assess the risk, a white dot will appear also. In the "plotmatrix_heat" sheet, all the risks IDs are written in the corresponding case, colored as per the defined thresholds. Currently only the first assessment is displayed
Mitigation measures
If you are interested in potential mitigation measures, we listed some measures in the risk register. You can access the online version here: https://www.georisk-project.eu/register/; we also provide dedicated links in either the risk identification sheet or the risk assessment sheet (in the re-assessment table)